## Sheet1
Time Plan: | Version | SOP* | What will be included: | Reason:
| Alfa Version | End of Q2 | `- Base program - Tab Action - Tab Quantity - Tab STK | Free testing - Users can create all what need for testing programs if works good and for learn all new future
| Alfa Version | During Q3** | `- Tab Statistic - Raporting - Tab Summary - Add new futures to Release Tab (if somethign will be missing) - correct all bugs find during Alfa tests | Free testing - Users can create all what need for testing programs if works good and for learn all new future
| Beta Version | End of Q3** | Clone data base from current programs to new | Tests all functions and compare results with SAT 1.0 programs.
| Beta Version | During Q4** | Correct all find bugs durign Beta Testing | Tests all functions and compare results with SAT 1.0 programs.
| Final Version | End Q4** | Start using SAT 2.0, Close work with SAT 1.0 | Opening the champagne
* Sop can be changing, depending of action in "normal" work and quality
** Sop can be changing, depending of progress in the previous phases